AI BUSINESS AUDIT

Revenue & Operations
Readiness Report

A practical diagnosis of where leads, follow-up and operational capacity are leaking revenue.

PREPARED FOR

BrightSpark Electrical

Electricians & Small Electrical Contractors

| 6.2 READINESS SCORE | 3 PRIORITY LEAKS | 30 days FIRST ACTION HORIZON |
| --- | --- | --- |

DESIGN PROTOTYPE

Illustrative content only. Final reports are generated from the customer’s assessment evidence.

01 | EXECUTIVE DIAGNOSIS

# The business has demand. The leakage is happening after the enquiry arrives.

BrightSpark Electrical appears to have a healthy flow of referral and Google enquiries, but the current response and quote-follow-up process depends too heavily on whoever is available at the time. The result is not a lack of leads; it is inconsistent conversion of the leads already being paid for.

HIGHEST-IMPACT ISSUE Warm enquiries and issued quotes are not being followed through consistently. Missed calls are returned manually, quote reminders are not owned by one role, and there is no reliable view of how many opportunities go cold. This creates invisible revenue loss and makes marketing performance look weaker than it may actually be.

## What matters most now

| 1 | Recover missed enquiries quickly Create an immediate text-back and clear callback ownership for calls that are not answered. |
| --- | --- |

| 2 | Make quote follow-up systematic Use a simple two-step follow-up sequence with visible status and a named owner. |
| --- | --- |

| 3 | Close the loop after completed work Trigger review requests and next-step prompts while customer satisfaction is highest. |
| --- | --- |

## Assessment confidence

High. The priority issues are specific, commercially relevant, and can be improved without replacing the entire software stack.

02 | READINESS PROFILE

# A capable business with inconsistent commercial follow-through

| 6.2 OVERALL | 5 LEAD RESPONSE | 4 FOLLOW-UP | 7 PROCESS CLARITY | 7 CUSTOMER EXPERIENCE |
| --- | --- | --- | --- | --- |

## Where the business is already strong

A clear service offer and strong local reputation create genuine enquiry demand.

The team uses established job-management and accounting tools rather than relying entirely on paper.

Customers receive competent service once a job is booked and allocated.

## Where revenue is most exposed

After-hours and busy-period calls rely on manual callbacks, with no immediate acknowledgement to the customer.

Quote follow-up varies by staff member and is not measured as a conversion stage.

Review requests and future-work prompts happen inconsistently after completed jobs.

COMMERCIAL INTERPRETATION The first investment should improve conversion, not generate more traffic. Until missed calls and quotes are followed through consistently, increasing ad spend risks feeding more opportunities into the same leakage points.

03 | DIAGNOSTIC FINDINGS

# Evidence-backed issues, ordered by commercial impact

| RED | Lead response Current state: After-hours and overflow handling is reactive. The owner or office team returns calls when capacity allows. Likely impact: Urgent customers often call the next electrician quickly. Even a modest number of unrecovered calls can represent significant lost job value. Fastest win: Send an immediate branded text acknowledgement and assign callback ownership. |
| --- | --- |

| RED | Quote follow-up Current state: Quotes are sent, but follow-up timing and ownership are inconsistent. Conversion is not visible in one place. Likely impact: Warm prospects can drift to competitors, while the business cannot distinguish price objections from simple lack of follow-up. Fastest win: Introduce two scheduled follow-ups and a clear won/lost outcome. |
| --- | --- |

| YELLOW | Workflow visibility Current state: Core tools are in place, but staff still rely on memory and manual checking to know what needs attention. Likely impact: The system works while key people are present, but tasks can stall during busy periods or absences. Fastest win: Create one daily view of uncontacted leads, open quotes and jobs awaiting customer action. |
| --- | --- |

| YELLOW | Reviews and repeat work Current state: Happy customers are not consistently prompted for a review or relevant future service. Likely impact: The business misses low-cost reputation growth and repeat-work opportunities after successful jobs. Fastest win: Trigger a review request after job completion and add one relevant next-step prompt. |
| --- | --- |

04 | 30-DAY ACTION PLAN

# Fix the fastest revenue leaks before adding complexity

| 1 | Days 1–7 ¦ Missed-call recovery Map the current call path, assign callback ownership, and launch an immediate text acknowledgement for unanswered calls. Track response time and recovered bookings. |
| --- | --- |

| 2 | Days 8–14 ¦ Quote follow-up Standardise follow-up at two agreed intervals, capture a simple status for every quote, and make open quotes visible to the responsible person. |
| --- | --- |

| 3 | Days 15–21 ¦ Review capture Send a short review request after completed jobs, with a direct link and one reminder when appropriate. |
| --- | --- |

| 4 | Days 22–30 ¦ Operating visibility Review the first month of missed calls, quote outcomes and review requests. Keep what works, remove friction, and decide whether deeper automation is justified. |
| --- | --- |

## Measures to track

| Measure | Initial standard |
| --- | --- |
| Missed calls acknowledged | Target: within 1 minute |
| Callback speed | Target: within 15 minutes during business hours |
| Quotes followed up | Target: 100% receive the agreed sequence |
| Quote outcomes recorded | Target: won, lost or pending |
| Review requests sent | Target: every eligible completed job |

05 | RECOMMENDED NEXT STEP

# Implement one contained commercial workflow and measure the result

The recommended first engagement is a focused follow-up sprint: missed-call recovery, quote follow-up and review capture. It should improve the handling of existing demand without requiring a full CRM replacement or a broad transformation program.

IMPLEMENTATION PRINCIPLE Automate the hand-off, not the relationship. Customers should still experience a capable local electrical business. Automation should make acknowledgement, reminders and visibility more reliable while people remain responsible for judgement and customer conversations.

## How this audit was prepared

This report is based on the discovery assessment provided by the business. Findings are limited to the evidence captured during that assessment and are prioritised by likely commercial impact, urgency, implementation effort and speed to visible improvement.

## Important note

The score is a decision aid, not a financial forecast. Any implementation should be confirmed against the business’s actual call volumes, quote data, software configuration and operating constraints.

AI Business Audit

Find the revenue leaks. Fix the highest-impact workflow first.

Prepared for discussion with Hugh.